Riipen Experience: Course Content Plan

Module content strategy for the 15-week course

Updated March 2026

Note on status: The module content for Weeks 1–6 is locked and reflected accurately below. Weeks 7–10 (Development phase) module content is provisional — a content architecture revision is in progress that will adjust module topics, time allocations, and the balance between module sections and embedded activity prompts. This document will be updated once Week 7–10 design docs are finalized. Weeks 11–15 are stable but have not yet been through detailed design doc review.

Overview

This document outlines the module content strategy for the 15-week Riipen Experience course. It serves as a content brief for module development — specifying what is taught each week, why, and how it connects to deliverables and competencies. The Course Structure document owns the structural picture (phases, deliverables, employer touchpoints); this document owns the module-level detail.

Content is designed to support competency development and project activities, with practical skills front-loaded and conceptual depth introduced when students have experience to connect it to.

Design Principles

1.  Variable module time based on need — Heavier content during orientation and skill-building weeks; lighter during production-intensive weeks

2.  Practical skills seeded early — Students need professional email, research skills, and team collaboration before the modules that go deep on those topics

3.  Just-in-time preparation — Content aligned to upcoming activities (kickoff prep before kickoff, feedback skills before progress review)

4.  Competency coverage verified — All NACE competency subskills explicitly addressed in module content

Time Budget

•  Total module content: ~13 hours across 15 weeks

•  Weekly course total: ~9 hours (3-credit course)

•  Balance: As module time decreases in later weeks, project work time increases

Content Functions

Module content serves five distinct functions:

| Function | Description | Example |
| --- | --- | --- |
| Orientation | What is this course? How does experiential learning work? | Week 1 |
| Skill-building | How do I do [specific thing] well? | Research, communication, feedback, presentation |
| Just-in-time prep | What do I need to know for [upcoming activity]? | Kickoff prep, progress review prep |
| Conceptual framework | How do I make sense of what I'm experiencing? | Ambiguity, theory-practice connection, transfer |
| Reflection scaffolding | How do I reflect meaningfully using DEAL? | Weeks 3, 6, 9, 12, 15 |

Week-by-Week Content Plan

Phase 1: Foundation (Weeks 1–3)

Week 1: Getting Started

Module Time: 90 minutes (Heavy)

Primary Function: Orientation + Practical skill-building

| Section | Time | Content |
| --- | --- | --- |
| What Is Experiential Learning? | 20 min | Brief orientation: how this course differs from traditional courses, the learning cycle, what's expected of you |
| Course Structure & Expectations | 15 min | 15-week arc, deliverables, employer touchpoints, how you'll be assessed |
| Creating an Effective Team Charter | 25 min | Why charters matter, what to include, how to have the conversation; includes reliability/dependability and contribution expectations |
| Time Management for Project Work | 20 min | Managing ongoing work (not cramming), prioritization basics, working with teammates across schedules |
| Professional Email Basics | 10 min | Quick intro: structure, tone, when to email vs. other channels; examples of good/bad emails |

Competencies Supported:

•  Teamwork: Reliability, Collaborative contribution, Shared accountability (via charter content)

•  Professionalism: Dependability (via time management)

•  Critical Thinking: Prioritization (via time management)

•  Communication: Professional correspondence (intro)

Deliverable Connection: Student Intake Questionnaire (Checkpoint)

Week 2: Preparing for Your Client

Module Time: 75 minutes (Medium-Heavy)

Primary Function: Skill-building (Research) + Just-in-time (Kickoff prep)

| Section | Time | Content |
| --- | --- | --- |
| Researching an Organization | 25 min | What to look for, where to find it, how deep to go; industry context, company specifics, recent news |
| Preparing for a Client Meeting | 20 min | What makes a kickoff successful, setting agenda, role assignments for the meeting |
| Asking Good Questions | 15 min | Open vs. closed questions, questions that clarify vs. questions that impress, prioritizing your questions |
| Active Listening in Client Meetings | 15 min | How to listen (not just wait to talk), note-taking strategies, clarifying without interrupting |

Competencies Supported:

•  Critical Thinking: Research and analysis

•  Communication: Active listening, Professional correspondence

•  Professionalism: Initiative (via preparation)

Deliverable Connection: Team Charter + Employer Outreach Email (Checkpoint)

Week 3: Understanding Your Client

Module Time: 45 minutes (Light)

Primary Function: Processing + Skill reinforcement

| Section | Time | Content |
| --- | --- | --- |
| Processing What You Learned | 20 min | Turning meeting notes into shared understanding, identifying what you learned vs. what's still unclear |
| Following Up Professionally | 15 min | The post-meeting email, confirming understanding, asking clarifying questions after the fact |
| Identifying Gaps and Ambiguity | 10 min | What don't you know yet? What assumptions are you making? Setting up research priorities |

Competencies Supported:

•  Communication: Written clarity, Active listening (reinforcement)

•  Critical Thinking: Problem framing (early exposure)

Deliverable Connection: Kickoff Summary (Checkpoint) + Reflection #1 (GRADED)

Note: Light module time because students just had their kickoff meeting — they have substantial processing, research, and reflection work to do. The DEAL framework is introduced in the Week 1 orientation content; Reflection #1 is the first application of that framework. The DEAL reference sheet and a pro tip on using AI for reflection are embedded in the Reflection #1 assignment prompt.

Phase 2: Discovery (Weeks 4–6)

Week 4: From Research to Strategy

Module Time: 60 minutes (Medium)

Primary Function: Skill-building (Analysis)

| Section | Time | Content |
| --- | --- | --- |
| Synthesizing Research into Insights | 20 min | Moving from "what we found" to "what it means," identifying patterns, drawing conclusions |
| Evidence-Based Reasoning | 15 min | What counts as evidence? Supporting claims vs. making assertions. Acknowledging uncertainty |
| Developing Your Approach | 15 min | From insights to strategy, defining what you'll deliver and how |
| Prioritization in Planning | 10 min | You can't do everything — what matters most? Scoping to reality, making tradeoffs explicit |

Competencies Supported:

•  Critical Thinking: Research and analysis, Evidence-based reasoning, Problem framing, Prioritization

•  Communication: Written clarity

Deliverable Connection: Context Analysis & Project Plan (GRADED)

Week 5: Direction Check Preparation

Module Time: 45 minutes (Light)

Primary Function: Skill-building (Communication) + Just-in-time (Direction Check)

| Section | Time | Content |
| --- | --- | --- |
| Communicating Your Approach | 15 min | Presenting a plan for validation, framing recommendations, inviting feedback |
| Managing Expectations | 15 min | What to do when scope shifts, delivering difficult messages, saying "we can't do that" professionally |
| Preparing for Direction Check | 15 min | What to present, what questions to ask, how to use this touchpoint effectively |

Competencies Supported:

•  Communication: Professional correspondence, Oral presentation (light)

•  Professionalism: Initiative, Feedback reception (setup)

Deliverable Connection: Direction Check Summary (Checkpoint)

Week 6: Working Through Ambiguity

Module Time: 60 minutes (Medium)

Primary Function: Skill-building + Conceptual framework + Reflection scaffolding

| Section | Time | Content |
| --- | --- | --- |
| Making Progress Under Uncertainty | 20 min | How to draft with incomplete information, when to keep researching vs. start writing, how to flag a blocker without stalling the team |
| From Research to Draft | 20 min | Organizing notes, building outlines, moving into production; AI use cases for synthesis and gap identification |
| Navigating Disagreement with Teammates and Clients | 20 min | Disagreeing productively during production; when to defer to employer direction vs. push back gracefully |

Competencies Supported:

•  Professionalism: Initiative, Feedback reception

•  Critical Thinking: Prioritization, Problem framing

•  Career & Self-Development: Reflection, Growth orientation

•  Communication: Written clarity

Deliverable Connection: Reflection #2 (GRADED)

Phase 3: Development (Weeks 7–10)

Provisional — see status note at top of document. The module topics, section content, and time allocations below reflect the original content plan. A revision is in progress that will add production skill content, rebalance module time across the phase, and move some elements from module sections to embedded activity prompts. Do not use this section as a final content brief until Week 7–10 design docs are complete.

Week 7: Giving and Receiving Feedback

Module Time: 60 minutes (Medium) — provisional

Primary Function: Skill-building (Feedback)

| Section | Time | Content |
| --- | --- | --- |
| Why Feedback Feels Hard | 15 min | The feedback paradox, identity triggers, why defensiveness is natural but counterproductive |
| Receiving Feedback Well | 20 min | A protocol: Listen → Clarify → Acknowledge → Decide later. Separating truth from relationship from identity |
| Giving Useful Feedback | 15 min | Specific, behavioral, actionable, prioritized. Moving from "nice" to useful |
| Preparing for Progress Review | 10 min | Anticipating feedback, preparing questions, planning how to capture and process input |

Competencies Supported:

•  Professionalism: Feedback reception

•  Teamwork: Constructive feedback

•  Communication: Active listening

Deliverable Connection: Work-in-Progress Summary (Checkpoint)

Week 8: Making Feedback Useful

Module Time: 30 minutes (Light) — provisional

Primary Function: Skill application

| Section | Time | Content |
| --- | --- | --- |
| Processing the Feedback You Received | 15 min | Sorting feedback: what to act on, what to note, what to set aside. Making a feedback response plan |
| Iteration as a Skill | 15 min | Revision isn't failure — it's the process. How professionals iterate |

Competencies Supported:

•  Professionalism: Feedback reception (application)

•  Critical Thinking: Prioritization (what feedback matters most)

Deliverable Connection: Peer Evaluation #1 (GRADED)

Note: Light module time because students just had Progress Review #1 — focus is on processing and applying feedback, plus completing peer evaluation. Revision likely to increase module time here given the density of what students are doing this week.

Week 9: Teamwork Under Pressure

Module Time: 45 minutes (Light-Medium) — provisional

Primary Function: Conceptual framework + Skill reinforcement

| Section | Time | Content |
| --- | --- | --- |
| Recalibrating Mid-Project | 15 min | Teams change under pressure. Reassessing roles, addressing dysfunction, renegotiating expectations |
| Addressing Peer Evaluation Feedback | 15 min | What did your peers tell you? How to have honest conversations about contribution |
| Shared Accountability When Stakes Rise | 15 min | Moving from "my part" to "our outcome," stepping up when team needs it, asking for help |

Competencies Supported:

•  Teamwork: Reliability, Collaborative contribution, Shared accountability (all reinforced/recalibrated)

•  Communication: Active listening (in difficult conversations)

Deliverable Connection: Draft Deliverable (Checkpoint)

Note: This is NOT introducing teamwork concepts — students have been collaborating for 8 weeks. This is about recalibrating when things aren't working.

Week 10: Connecting Theory and Practice

Module Time: 60 minutes (Medium) — provisional

Primary Function: Conceptual framework + Reflection scaffolding

| Section | Time | Content |
| --- | --- | --- |
| What Are You Actually Learning? | 20 min | Surfacing tacit learning, naming skills you're developing, connecting daily work to competencies |
| From Experience to Concept | 20 min | How to extract principles from specific situations, what makes learning transferable |
| DEAL Reflection: Going Deeper | 20 min | Moving beyond description, examining assumptions and decisions, articulating learning that will stick |

Competencies Supported:

•  Career & Self-Development: Self-awareness, Reflection, Growth orientation

•  Critical Thinking: Evidence-based reasoning (in reflection)

Deliverable Connection: Reflection #3 (GRADED)

Phase 4: Refinement (Weeks 11–13)

Week 11: Quality and Craft

Module Time: 45 minutes (Light-Medium)

Primary Function: Skill-building (Quality) + Just-in-time (Progress Review #3)

| Section | Time | Content |
| --- | --- | --- |
| What Does "Quality" Mean? | 15 min | Standards for professional work, attention to detail, the difference between "done" and "polished" |
| Self-Review Before Client Review | 15 min | Catching errors, checking alignment with requirements, reviewing with fresh eyes |
| Preparing for Progress Review #3 | 15 min | This is near-final work — what kind of feedback do you need now? |

Competencies Supported:

•  Professionalism: Quality and attention to detail

•  Critical Thinking: Prioritization (what to refine vs. leave alone)

Deliverable Connection: Near-Final Package (Checkpoint)

Week 12: From Feedback to Final

Module Time: 60 minutes (Medium)

Primary Function: Skill-building (Presentation) + Just-in-time + Reflection scaffolding

| Section | Time | Content |
| --- | --- | --- |
| Final Iteration | 15 min | Incorporating final feedback, knowing when to stop, avoiding last-minute chaos |
| Presentation Fundamentals | 25 min | Structure, visual design basics, speaking to clients vs. academic audiences |
| Planning Your Presentation | 20 min | Who presents what, handling Q&A, practicing effectively |

Competencies Supported:

•  Communication: Oral presentation

•  Professionalism: Quality and attention to detail

•  Career & Self-Development: Reflection, Growth orientation

Deliverable Connection: Presentation Outline (Checkpoint) + Reflection #4 (GRADED)

Week 13: Finalizing Deliverables

Module Time: 20 minutes (Minimal)

Primary Function: Just-in-time (Final push)

| Section | Time | Content |
| --- | --- | --- |
| Final Deliverable Checklist | 10 min | What to check before submitting, common mistakes, the Change Log requirement |
| The Home Stretch | 10 min | Brief motivational/mindset content — you're almost there, finishing strong |

Competencies Supported:

•  Professionalism: Quality and attention to detail, Dependability

Deliverable Connection: Final Deliverables (GRADED)

Note: Minimal module time — students know what to do, they need time to do it.

Phase 5: Integration (Weeks 14–15)

Week 14: Presenting Your Work

Module Time: 30 minutes (Light)

Primary Function: Just-in-time (Presentation prep)

| Section | Time | Content |
| --- | --- | --- |
| Presentation Day Prep | 15 min | Mindset, handling nerves, final run-through tips |
| Handling Q&A | 15 min | Responding to questions you can't answer, thinking on your feet, staying professional under pressure |

Competencies Supported:

•  Communication: Oral presentation, Active listening

•  Professionalism: Initiative (handling unexpected questions)

Deliverable Connection: Presentation Prep (Checkpoint)

Week 15: Transfer and What's Next

Module Time: 60 minutes (Medium)

Primary Function: Conceptual framework + Reflection scaffolding

| Section | Time | Content |
| --- | --- | --- |
| What Did You Learn? | 20 min | Looking back at the full arc, identifying growth, naming what changed |
| Transfer: Taking It With You | 20 min | How to apply this learning in future contexts, identifying transferable principles |
| Articulating Your Experience | 20 min | How to talk about this experience in interviews, on resumes, in professional contexts; DEAL for final reflection |

Competencies Supported:

•  Career & Self-Development: Self-awareness, Reflection, Growth orientation, Career articulation

•  Communication: Oral presentation (articulating experience)

Deliverable Connection: Final Presentation + Peer Evaluation #2 + Reflection #5 (GRADED)

Competency Coverage Summary

Communication

| Subskill | Primary Coverage | Secondary Coverage |
| --- | --- | --- |
| Written clarity | Week 4 (Research to Strategy) | Weeks 3, 5 (professional correspondence) |
| Oral presentation | Weeks 12, 14 (Presentation) | Week 5 (Direction Check) |
| Professional correspondence | Week 1 (intro), Week 5 (depth) | Weeks 2, 3 (application) |
| Active listening | Weeks 2, 3 (client meetings) | Week 7 (feedback conversations) |

Critical Thinking

| Subskill | Primary Coverage | Secondary Coverage |
| --- | --- | --- |
| Problem framing | Week 4 (Research to Strategy) | Week 3 (identifying gaps) |
| Research and analysis | Weeks 2, 4 | — |
| Evidence-based reasoning | Week 4 (explicit) | Week 10 (in reflection) |
| Prioritization | Week 1 (time management), Week 4 (planning) | Week 8 (feedback prioritization) |

Teamwork

| Subskill | Primary Coverage | Secondary Coverage |
| --- | --- | --- |
| Reliability | Week 1 (team charter) | Week 9 (recalibration) |
| Collaborative contribution | Week 1 (expectations), Week 9 (recalibration) | — |
| Constructive feedback | Week 7 (Giving and Receiving Feedback) | — |
| Shared accountability | Week 1 (team charter), Week 9 (recalibration) | — |

Professionalism

| Subskill | Primary Coverage | Secondary Coverage |
| --- | --- | --- |
| Dependability | Week 1 (time management, charter) | — |
| Quality and attention to detail | Week 11 (Quality and Craft) | Week 13 (checklist) |
| Initiative | Week 6 (Working Through Ambiguity) | Week 2 (preparation) |
| Feedback reception | Weeks 7, 8 (Feedback modules) | — |

Career & Self-Development

| Subskill | Primary Coverage | Secondary Coverage |
| --- | --- | --- |
| Self-awareness | Weeks 3, 6, 9, 12, 15 (DEAL reflections) | — |
| Reflection | Weeks 3, 6, 9, 12, 15 (DEAL reflections) | — |
| Growth orientation | Weeks 3, 6, 9, 12, 15 (DEAL reflections) | — |
| Career articulation | Week 15 (Transfer and What's Next) | — |

Module Time Summary

| Week | Module Topic | Time | Load |
| --- | --- | --- | --- |
| 1 | Getting Started | 90 min | Heavy |
| 2 | Preparing for Your Client | 75 min | Medium-Heavy |
| 3 | Understanding Your Client | 45 min | Light |
| 4 | From Research to Strategy | 60 min | Medium |
| 5 | Direction Check Preparation | 45 min | Light |
| 6 | Working Through Ambiguity | 60 min | Medium |
| 7 | Giving and Receiving Feedback | 60 min | Medium (provisional) |
| 8 | Making Feedback Useful | 30 min | Light (provisional) |
| 9 | Teamwork Under Pressure | 45 min | Light-Medium (provisional) |
| 10 | Connecting Theory and Practice | 60 min | Medium (provisional) |
| 11 | Quality and Craft | 45 min | Light-Medium |
| 12 | From Feedback to Final | 60 min | Medium |
| 13 | Finalizing Deliverables | 20 min | Minimal |
| 14 | Presenting Your Work | 30 min | Light |
| 15 | Transfer and What's Next | 60 min | Medium |

Total Module Content: ~13 hours (785 minutes) (total will update when Weeks 7–10 are finalized)

Resource Library (Supplementary)

In addition to module content, students have access to standalone reference resources:

| Resource | Description | When Introduced |
| --- | --- | --- |
| Professional Email Templates | Examples of good emails for common situations | Week 1 |
| Team Charter Template | Structured template with prompts | Week 1 |
| Meeting Prep Checklist | What to do before any client meeting | Week 2 |
| Research Source Guide | Where to find information about organizations | Week 2 |
| DEAL Reflection Guide | Detailed guidance on the reflection model | Week 3 |
| Feedback Protocol Card | Quick reference for giving/receiving feedback | Week 7 |
| Quality Checklist | Pre-submission review checklist | Week 11 |
| Presentation Checklist | Preparation checklist for final presentation | Week 12 |

Notes for Implementation

1.  Module content is asynchronous — All videos, readings, and light activities are self-paced

2.  Reflection scaffolding is distributed across the course — DEAL is introduced in Week 1 orientation content and applied at Weeks 3, 6, 9, 12, and 15; deeper DEAL scaffolding modules land at Weeks 6 and 10

3.  Practical skills come before conceptual depth — Email basics in Week 1, deeper communication strategy in Week 5

4.  Light weeks = heavy production — When module time decreases, project work time increases

5.  Content prepares for upcoming activities — Feedback content before Progress Review, presentation content before Final Presentation

6.  Some content delivered as embedded activity prompts — Not all skills warrant a module section; standing prompts in weekly activities (e.g., weekly progress check-ins, Change Log maintenance) deliver recurring professional habits without module overhead